Agenda Item 1.5.1

Action Log

JOINT COMMITTEE MEETING

Update for meeting on 6 September 2022

| Minute | ACTIONS | Lead | Progress |
| --- | --- | --- | --- |
| July 2022 |
| EASC 22/79 | EASC Action Plan Add information relating to immediate release Focus on the increasing number of long wait handovers | EASCT / WAST | Not yet added anticipated Sept Completed |
|  | Different staff input to WAST Control / call options Potential to consider social care, care homes and maternity | WAST | To be confirmed |
|  | Red Demand and Variation Further work with Optima leading to a presentation at a future meeting to understand the drivers of variation in red performance | EASCT / WAST | Red report received Variation presentation TBC |
| EASC 22/81 | Roster Reviews Provide actual numbers of staff and resources on a health board by health board basis at the next meeting | WAST | WAST Provider Report |
|  | Changes to WAST working practices Indicative timescales to be included in the WAST provider report | WAST | WAST Provider Report |
|  | Immediate Red Release Protocol drafted by WAST language to be amended and re-circulated to Members Members to take through local governance processes | WAST Members | Completed To be confirmed |
| EASC 22/82 | EMRTS Cymru and Wales Air Ambulance Charity Discussions regarding co-locating services to be held | Jason Killens | Focus on Session TBC |
|  | Temporary Funding £3m (non-recurrent) Progress on recruitment, utilisation and impact to be reported at the next meeting | WAST | WAST Provider Report |
| EASC 22/83 | Emergency Ambulance Services Commissioning Framework Further joint working with WAST and HBs to finalise the Framework and submit for approval | EASCT | Agenda item |
| May 2022 |
| EASC22/59 | Deep-dive in to red performance ‘Deep-dive’ into red performance to be shared with members and considered in more detail at the EASC Management Group held on 16 June (completed) | WAST | Completed |
|  | Immediate release The need to re-consider and agree a system-wide position for ‘immediate release requests’ from the ambulance service with release refusal to be considered a ‘never event’ | All | Completed |
|  | ‘Plan B’ Develop a ‘plan B’ via the EASC Management Group in order to address the current position and patient safety risks across the system for presentation to EASC Committee | EASC Management Group | Completed (EASC Action Plan) |
| EASC 22/62 and 64 | EMS Commissioning Framework The new Commissioning Framework to be presented to the next meeting of the EASC Management Group and to be received at the next EAS Joint Committee meeting for approval | CASC | Agenda item 2.6 |
| EASC22/62 | NHS Wales Delivery Unit – Appendix B Report EASC Management Group to establish a task and finish group that would review the Appendix B process and agree a way forward | DASC | Completed |
| EASC22/63 | Chair’s Summary Chair’s Summary to be produced after each sub-group meeting to mirror the arrangements of the EAS Joint Committee | DCASC | Completed |
| EASC22/64 | EASC IMTP Quarterly update with regard progress made against the IMTP to be provided going forward | DCASC | Agenda item 2.7 Commissioning Update |
| March 2022 |
| EASC22/20 | Performance Report Digital Health and Care Wales looking at linked data sets related to patient outcomes and would report findings at a future meeting | DCASC | Meeting held with DHCW and WAST Document developed - complicated data / ongoing |
|  | Actions agreed for all: maximise temporary additional front-line ambulance capacity during the coming period including overtime and WAST to operate at a higher state of emergency alert to maximise front-line resource use of the agreed whole system escalation process and the actions taken health board resources in place such as same day emergency care, urgent primary care centres, flow centres or communication hub etc and identify two or three deliverables as part of this Handover Improvement Plan. This would include managing or challenging slippage and monitoring the impact on the patient experience and recognised the need to move at pace. | WAST HBs HBs HBs | Performance Report developed completed / ongoing |
|  | Requirements for WAST reducing sickness and setting the required improvement trajectory agreeing timescales for reducing post-production lost hours and managing the inefficiency in the system ensuring all roster changes would be in place by end of November 2022 reducing the variation within the service by adopting good operational practice on a day by day basis | WAST | WAST Update Report Completed / ongoing |
| January 2022 |
| EASC 22/10 | Key Reports and Updates WAST to develop a system that will capture and report on episodes where ambulance services are not able to deploy a response vehicle or where the patient finds own transport to hospital – link to electronic case card | WAST | Updated July 2022 Further information to be provided |
| May 2021 |
| EASC 21/26 | Committee Effectiveness Discussion re wider membership with patient voice or additional independent members | Chair | Discussion planned with Citizens Voice Body |

CASC